## Cover Page
<Project Name>
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
Project ID: Car Servicing | <Batch code/project id> |  |  | <SCI.ID> / Ver: <No.>
C3: Protected
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog <Instructions> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Sprint 1/2
The Sprint sheets has to be filled for each sprint
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
| Feature Id | List the feature id taken from product backlog that are selected to be completed in the particular sprint.
| Task No | List the number tasks the feature is split into.
| Task | Name the tasks the feature is split into.
| Owner | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5/6 | Task done in Day1/2/3/4/5/6 - Sprint review and retrospective to be held on Day 6
| Total | Summation of the estimation of the per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint 1
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
FS1 | 1 | User Registration | Abhishek | 1 | 1 | [5 empty] | Completed
FS1 | 2 | Shop Manager Registration | Abhishek | 1 | 1 | [5 empty] | Completed
FS1 | 3 | Registration UI | Abhishek | 1 | 1 | [5 empty] | Completed
FS2 | 1 | User Login | Abhishek | 1 | 1 | [5 empty] | Completed
FS2 | 2 | Shop Manager Login | Abhishek | 1 |  | 1 |  |  |  |  | Completed
FS2 | 3 | Login UI | Abhishek | 1 |  | 1 |  |  |  |  | Completed
FS3 | 1 | Superuser Approve and Deny Manager | Abhishek | 1 |  | 1 |  |  |  |  | Completed
FS3 | 2 | Superuser Approve and Deny UI | Abhishek | 1 |  | 1 |  |  |  |  | Completed
FS4 | 1 | Getting All Product Details Backend | Abhishek | 1 |  |  | 1 |  |  |  | Completed
FS4 | 2 | Displaying Products UI | Abhishek | 1 |  |  | 1 |  |  |  | Completed
FS5 | 1 | Search/Sort Products | Abhishek | 1 |  |  | 1 |  |  |  | Completed
FS5 | 2 | Search/Sort Products UI | Abhishek | 1 |  |  | 1 |  |  |  | Completed
FS6 | 1 | Edit/Add Products | Abhishek | 1 |  |  |  | 1 |  |  | Completed
FS6 | 2 | Edit/Add Products UI | Abhishek | 1 |  |  |  | 1 |  |  | Completed
FS7 | 1 | Product Location Details | Abhishek | 1 |  |  |  | 1 |  |  | Completed
FS7 | 2 | Product Location UI | Abhishek | 1 |  |  |  | 1 |  |  | Completed
FS8 | 1 | Billing - Backend | Abhishek | 1 |  |  |  |  | 1 |  | Completed
FS8 | 2 | Billing UI | Abhishek | 1 |  |  |  |  | 1 |  | Completed
FS9 | 1 | Purchase History Backend | Abhishek | 1 |  |  |  |  | 1 |  | Completed
FS9 | 2 | Purchase History UI | Abhishek | 1 | [5 empty] | 1 | Completed
FS10 | 1 | Logout | Abhishek | 1 | [5 empty] | 1 | Completed
FS10 | 2 | LogoutUI | Abhishek | [6 empty] | 1 | Completed
|  | Total |  | 21 | 4 | 4 | 4 | 4 | 3 | 3
Sprint Goal
Some sprint goal

## Sprint 2
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
|  | Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal
Some sprint goal

## Data (hidden)
In-Progress
Completed
N/A